## charter
Project Charter - Communications, Engagement and PMO
Date |  | 2015-09-17 | Project |  |  | Comms and Engagement |  | Sponsor 1 |  | Loretta Outhwaite
Project Leads |  | Paul Savill, Andy Holleborn, Andy Newman, Zoryna O'Donnell | [5 empty] | Project Manager |  | TBC
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
My Life A Full Life (MLAFL) is about organisations working together in partnership with the voluntary sector, the Isle of Wight Clinical Commissioning Group (CCG), the Isle of Wight Council (IWC), the Isle of Wight NHS Trust (IWNHS Trust) and One Wight Health (a GP membership organisation) providing for peoples individual needs to enable them to take control of their lives and plan for their future health and social care needs. Communications, engagement and PMO workstream will develop and implement a strategy that not only are all stakeholders informed and involved in deciding what their model of care looks like be deliver change at pace and keep to key milestones. |  |  | IN | All communications and engagement relating to My Life programme workstreams. Implementation of communication and engagement strategy for; - Islanders, island organisations and visitors -National and regional stakeholders such as NHS England, Trust Development Authority -My Life partner organsiations, their staff and volunteers
|  |  | OUT | Everything that is not relating to the My Life workstream.
Objectives
1. To deliver the communications, engagement and PMO function to suppoirt the delivery of the value proposition. 2. To engage and re-ignate the key stakeholders by using clear and audience appropriate language and channels of communication. 3. To ensure that a whole system communication is co-produced and developed with local people. 4. To develop a centralised PMO Hub to co-ordinate all activity of the value proposition accross organisations. This is particularly important because we have a dispersed workforce of up to 10,000 accross numerous partner organisations and sites as well as diverse communities.
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls | Rating
Achieving set milestones for the work stream within agreed timescales and budget |  |  |  | Delay in release of funding resulted in slippage of timeline. | An updated timeline and schedule of work will be prepared for this and other workstreams |  |  | Outcomes | Failure to communicate, engage and co-produce effectively |  | Strong governance, accountability, perf. monitoring (weekly), involvement of VCS, use of toolkits and good practice guidance | G
A minimum of 50% of activities and products within this work stream are co-produced |  |  |  |  | Aiming for 75% by 2017 |  |  | Cost | Ineffectiveness of this workstream can have a negative impact on other work stream's ability to deliver the required efficiency savings |  | Identifying and managing all interdependencies proactively | A
PMO response time is 5 working days |  |  |  | PMO is still being developed | Aim to fully establish PMO function by 30/10/15 |  |  | Performance | Lack of capacity |  | Recruitment of staff - subject to Vanguard funding | A
Every issue of staff newsletter across all partner organisations contains a programme update |  |  |  |  | 100% compliance |  |  | Safety | Reputational risk |  | Strong governance, accountability, perf. monitoring (weekly), involvement of VCS, use of toolkits and good practice guidance | A
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
what activities will be completed;
visual representation;
Our approach to communications, engagement and PMO includes; :
1. Strong partnership and co-production approach, including integration of communications across partner organisations
2. Robust programme management (PMO) and governance as well as standardisation (documents, toolkits, processes etc)
3. Development and implementation of comms and engagement strategy which fully utilises all available internal and external channels such as newsletters, media, user groups, democratic forums
4. Effective programme management to ensure mutual support and commitment across and between the work streams from the workstreams participants and the organisations they represent
5. Working close with evaluation workstream to ensure quality assurance and measuring outcomes
Approach
Activities
KPI's will be reviewed with evaluation workstream lead, outcomes and metrics will be determined via logic modelling framework