## charter
Project Charter - Evaluation and Measurement
Date |  | 2015-09-14 | Project |  |  | MLAFL Evaluation |  | Sponsor 1 |  | Rida Elkheir |  | Sponsor 2
Project Lead |  | Sharon Kingsman | Project Manager |  |  | Sharon Kingsman |  | Project Support |  | to be recruited |  | to be recruited
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
We have created a strong My Life a Full Life programme and brand on the Isle of Wight. Our new care model is aimed at improving health and wellbeing and care and quality outcomes, delivering more care at home and in the community and making health and wellbeing financially sustainable. With reduced finances and an increasing proportion of older people the current models of care are not sustainable. 10 work streams have been created one of which is the evaluation and measurement work stream. The focus is on evaluating the difference MLAFL has made to people, their carers and families as well as to the health and care system culture and how we all work to provide integrated care. This workstream will set a framework to evaluate outcomes of the workstreams. |  |  | IN | To evaluate below workstreams and some of their sub-projects; 1- Prevention and Early Intervention 2- Whole Integrated System Review 3- Integrated Locality Teams 4- Integrated Access 5- Workforce Development 6- Communications, engagement and PMO 7- Strategic Commissioning - depends on resource availability
|  |  | OUT | IT and estates Organisational integration and form Performance monitoring of any workstream
Objectives
To evaluate the work streams with regard to the extent to which they have contributed to; 1) A change in organsational culture 2) A change in the way the health and social care system on the Isle of Wight operates i.e. Is it more integrated? Is it delivered closer to where people live? 3) A change in user experience i.e. Does the person feel they are at the centre of their care? 4) A change in the experience of carers 5) A change in our work force; training, development , sickness absense 6) A change in how people are enabled to better self care or self manage their health and wellbeing. Secondary objectives: to add to the body of knowledge regarding evaluation of health and social care
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  | Rating
Seven work streams and major project has a logic model |  |  |  | 5% | 100% |  |  | Outcomes
Key metrics that are already collected are identified |  |  |  |  | 100% |  |  | Cost | Monies are not available |  | Clarification on timescales for money draw down. |  | A
Robust tools to gather qualitative data are developed |  |  |  | 5% | 100% |  |  | Performance | Lack of capacity to carry out the evaluation |  | Recruit 2 analysts - 1 quantitative, 1 qualitative |  | R
Safety
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
Mixed Methodology based on a triangulation of evidence from quantitative, qualitative and financial data to give a full picture t of he the difference MLAFL has made to the health and social care system.
A realist appraoch which will consider the wider context factors such as funding and policy and the affect they have had on perception and behaviour in the delivery of new models of care.
Logic models will be developed with workstream leads to establish expected outcomes.
This will support work to identify metrics already gathered locally, gaps in data and to
develop qualitative methods of collecting staff and user experience.
This work will also support other workstream leads to consider performance indicators relevant to their own workstream.
Approach
Activities
Quantitative
Qualitative
Financial
Quantitative
Logic
Model and Evaluation Framework
Development
Qualitative
Financial
Agree metrics already collected
Develop data collecting tools
Establish baseline
Develop methods to collect quantitative data gaps
Collect and analyse data
Develop/implement financial modelling tools
Sept/Oct
Nov/Dec
Jan onwards

## charter (hidden)
Workstream/Project Charter - Evaluation and Measurement
Date |  | 2015-09-14 | Project |  |  | MLAFL Evaluation |  | Sponsor 1 |  | Rida Elkheir |  | Sponsor 2
Project Lead |  | Sharon Kingsman | Project Manager |  |  | Sharon Kingsman |  | Project Support |  | to be recruited |  | to be recruited
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
We have created a strong My Life a Full Life programme and brand on the Isle of Wight. Our new care model is aimed at improving health and wellbeing and care and quality outcomes, delivering more care at home and in the community and making health and wellbeing financially sustainable. With reduced finances and an increasing proportion of older people the current models of care are not sustainable. 10 work streams have been created one of which is the evaluation and measurement work stream. The focus is on evaluating the difference MLAFL has made to people, their carers and families as well as to the health and care system culture and how we all work to provide integrated care. background to the project; what is the current problem?; brief story so far - if continuation; what is the purpose?. |  |  | IN | Prevention and Early Intervention Whole Integrated System Review Integrated Locality Teams Integrated Access Work Force Development Communications, engagement and PMO
|  |  | OUT | IT and estates Strategic Commissioning Organisational integration and form
Objectives
To evaluate the work streams with regard to the extent to which they have contributed to; 1) A change in organsational culture 2) A change in the way the health and social care system on the Isle of Wight operates i.e. Is it more integrated? Is it delivered closer to where people live? 3) A change in user experience i.e. Does the person feel they are at the centre of their care? 4) A change in the experience of carers 5) A change in our work force; training, development , sickness absense 6) A change in how people are enabled to better self care or self manage their health and wellbeing.
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  | Rating
[8 empty] | Outcomes | Lack of capacity to carry out the evaluation |  | Recruit 2 analysts - 1 quantitative, 1 qualitative |  | R
[8 empty] | Cost | Moneys are not available |  | Clarification on timescales for money draw down. |  | A
[8 empty] | Performance |  |  |  |  | G
Safety
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
what activities will be ccompleted;
visual representation;
visual display of the approach / method / overview master schedule;
Approach
Activities