## Instructions
How to use this document
Overview The purpose of this document is to provide standard project management and funding request templates for use across the My Life a Full Life programme. These documents will be used by work-stream leads and sponsors to: - request funding from the MLaFL board in line with the requested Vanguard funding - provide assurance to the board that the delivery of benefits is being managed using a defined methodology - form the basis of weekly project management office ( PMO) meetings to track, support and escalate work-stream delivery See instructions below on how to complete these templates.
Tab | How it needs to be completed | Who needs to sign-off
1. Charter | One Charter is to be completed for the entire workstream | MLaFL board
2. Workstream schedule | One workstream schedule must be completed for each workstream | MLaFL board
3. Risks & issues log | One Risks & issues log must be completed for each work-stream | MLaFL board
4. Key Performance indicators | KPIs as required by each work-stream | MLaFL board
5. Finance Template | One template for each work-stream | MLaFL board
6. Finance Details | One template for each project - add tabs as required | MLaFL board
1. Charter | Guidance notes for the work-stream charter
2. Workstream schedule | Guidance notes for the work-stream schedule
3. Risks & issues log | Guidance notes for the Risks& issues log
4. Key Performance indicators | Guidance notes for KPIs
Multiple KPIs may be required
5.Finance template | Guidance on completign the finance template
6.Finance details | Guidance for completing the finance details document
work-stream title
actions/ tasks, owners , start end dates. Use links and 'foolows on from ' to indicate relations to other tasks
cells auto populate based on dates input
Red line shows current date- use 'back spikes to show delays.
work-stream name
Risk- a possible enent or circumstanced that will negatively impact work-stream delivery schedule. Issue- a problem that has occured
Action to be taken to address issue or mitigate risk
Action owner, due date, escalation and status of action- use RAG - red - risk still outstanding no mitigation; amber- mitigation in place;green - issue avoided
Use summary from work-stream charter
Detail of total vanguard and matched funding
The sum needed from the vanguard funding
Creat an indicative timelibe showing when the funds are needed and what for
Indicate if any future funding will be needed to further support the spend proposed
Describe and confirm that any funding governance guidelines are being followed
Describe and confirm the project management in place to ensure on time delivery of the funded work
Insert name of work-stream
Total funding required to carry out the proposed work, broken down into pay/ non-pay and captial spend. Spend shown over the next 4 years and note of any recurrence each year
The Vanguard / MLaFL component of the about amoutnrequested
Any matched funding for the planned work
Any differences between the current amount requested and work being proposed now and the value proposition
Outline what will take place to implement the change and achieve the objectives
High level timeline showing main milestones
Describe the back-ground - why we need to do this work
what's in and out of scope for this work-stream- include interdependencies
What are the main objectives of the work-stream- what are we trying to achieve
What you will measure to determine success, including a target for each measurement
Statement of the main risks to the work-stream delivering what it sets out to within any time and cost budget outlined

## 1. charter
Integrated Access
Start Date |  | 2015-09-08 | Project |  |  | Integrated Access |  | Sponsor 1 |  | Katie Gray |  | Sponsor 2 | Chris Mathews
Project Lead - IWC |  | Ian Lloyd | [5 empty] | Project Implementation Officer -
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
IN
OUT
Objectives
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  |  | Rating
Existing performance measures matched if not exceeded |  |  |  |  | 95% attainment across all performance measures |  |  | Quality | Failure to deliver quality outcomes |  | Processes / cross skilled training needs identified and fulfilled |  |  | A
Improved staff morale | [7 empty] | Cost | Savings identfied not delivered |  | Baseline budget to be undertaken. Future model developed using predecitive tools. |  |  | A
[8 empty] | Performance | Failute to maintain contractual performance |  | Ongoing monitoring and evaluation of impact. |  |  | G
[8 empty] | Safety | Critical emergency services compromised |  | Map and understand resources |  |  | G
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
Approach
Activities
The delivery of integrated access for the residents and visitors to the Isle of Wight will be achieved within two phases. The first phase will bring together the services currently located within the Intagrated Care Hub and also the Westridge Contact Centre. The secondary phase will identify additional services and organisations which will benefit inclusion within the integrated access. Once scoped delivery plans will be put in place to deliver and integrate these services.
Services for consideration;
Wight care (Telephony) SPARRCS
IWC Contact Centre District Nursing
999 Ambulance Crisis Responses
111 Non emergency
NHS Switchboard
Voluntary Sector
Adult First Response
Patient Transport
Access to Health and Social Care on the Isle of Wight is based within complex and confusing system, the current system has emerged over a period of time and as such there is no single point of access. People are often left bewildered and confused when attempting to navigate and gain access to the service they, or the person they are caring for require.
The My Life a Full Life (MLAFL) Board had requested an exploration of the integrated care hub and whether it could provide a single point of access to health and social care. It became apparent that discussions between senior officers within each organisation had also initiated the same work including additional service areas. Therefore this piece of work is now being led by the Council Organisational Change Team.
Mental Health Contact Service (Phase 2)
GP Contact Service (Phase 2)
Wightcare (Mobile Responders)
Any other Internal / External Service (Phase 2)
1. Move to an integrated access hub that has a single management structure and that utilises technologies to give a holistic, co-ordinated and consistent point of contact for all people.
2. Demonstrate and enable an improved experience/outcome for those accessing services that will enable calls to be transferred seamlessly across the sectors to the right person where appropriate through integration of community and emergency 24/7 service provision.
3. Work towards ensuring that there is one empowered people and workforce supported by the One Island £ that complies with the principles of : Resilience, Affordability ; Sustainability.
Review of current services and map potential areas of duplication
Identify additional services / organisations which would benefit inclusion within the integrated Access service .
Develop standard operating procedures, training packages and single management structure
Undertake training needs analysis and develop training packages to ensure consistency of skills sets across all sectors.
Develop performance metrics to ensure compliance against service, contractual and internal standards
Develop performance metrics across all services delivered within the integrated access
Agree both short and long term commissioning strategy. Develop formal legal partnership requirement if required.
Phase 1
Phase 2
Performance Indicators
Delivery
Scoping
Commissioning and Finance