## charter
One Leadership, Workforce and Organisational Development
Date |  | 2015-09-16 | Project |  |  | Leadership, Workforce &OD |  | Sponsor 1 |  | Claire Shand |  | Sponsor 2 | N/A
Project Leads |  | Cabrini Salter, Jacqui Skeel, Tracey Cartmell | [5 empty] | Project Support
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
Our staff will be increasingly required to work across boundaries with much closer collaboration between specialists and generalists, hospital and community and mental and physical health. Developing a preventative and integrative system culture will go hand in hand with an empowered workforce and high quality services. We also understand that system-wide leadership is critical to the success of My Life a Full Life. There is growing recognition that effective system leadership is a necessary pre-requisite to achieving truly effective care co-ordination. The Centre of Excellent will attract people to come and work on the Island. It's primary focus is about developing peoples skills for new roles in the new model of care. It will be an important part of their career development and will enable us to retain professionals in health and social care. |  |  | IN | All those working across the Island's Health and Social Care System, including Isle of Wight Council, NHS, CCG, voluntary sector, care homes, public health, social care, GP's. This workstream will develop training and leadership programmes for the workforce
|  |  | OUT | Workforce not involved with health and social care for Island people.
Objectives
This project aims to develop one workforce with the right resources, right skills in the right place. Our objectives are; 1- We will create one culture which is empowering, inspiring and motivating people to work together. 2- There will be one leadership with inspirational system leadership clearly paving a way forward and develop a 'centre of excellence' for recruiting and developing an excellent workforce. 3- Work with care home workforce and develop skills to deliver new model of care 4- We will create a Centre of Excellence for workforce development to up-skill and attract staff We are aiming to achieve below efficiencies • Improved skill-mix to provide staff with a wider skill-set and allow greater flexibility • Reducing duplication of work • Improved recruitment and retention
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  |  | Rating
[8 empty] | Outcomes | [5 empty] | R
[8 empty] | Cost | [5 empty] | A
[8 empty] | Performance | [5 empty] | G
Safety
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
This workstream will work with all health and social care organisations to develop skills through;
1- Develop and deliver training programmes such as action learning set, leadership development programmes
2- Develop centre of excellence
3- Work with care homes and deliver training to develop skill sets
to provide new model of care
4- Deliver leadership programmes
5-Develop health and social care apprenticeships programmes
Approach
Activities
Logic modelling outcomes?
Skilled workforce to deliver new model of care