## Instructions
How to use this document
Overview The purpose of this document is to provide standard project management and funding request templates for use across the My Life a Full Life programme. These documents will be used by work-stream leads and sponsors to: - request funding from the MLaFL board in line with the requested Vanguard funding - provide assurance to the board that the delivery of benefits is being managed using a defined methodology - form the basis of weekly project management office ( PMO) meetings to track, support and escalate work-stream delivery See instructions below on how to complete these templates.
Tab | How it needs to be completed | Who needs to sign-off
1. Charter | One Charter is to be completed for the entire workstream | MLaFL board
2. Workstream schedule | One workstream schedule must be completed for each workstream | MLaFL board
3. Risks & issues log | One Risks & issues log must be completed for each work-stream | MLaFL board
4. Key Performance indicators | KPIs as required by each work-stream | MLaFL board
5. Finance Template | One template for each work-stream | MLaFL board
6. Finance Details | One template for each project - add tabs as required | MLaFL board
1. Charter | Guidance notes for the work-stream charter
2. Workstream schedule | Guidance notes for the work-stream schedule
3. Risks & issues log | Guidance notes for the Risks& issues log
4. Key Performance indicators | Guidance notes for KPIs
Multiple KPIs may be required
5.Finance template | Guidance on completign the finance template
6.Finance details | Guidance for completing the finance details document
work-stream title
actions/ tasks, owners , start end dates. Use links and 'foolows on from ' to indicate relations to other tasks
cells auto populate based on dates input
Red line shows current date- use 'back spikes to show delays.
work-stream name
Risk- a possible enent or circumstanced that will negatively impact work-stream delivery schedule. Issue- a problem that has occured
Action to be taken to address issue or mitigate risk
Action owner, due date, escalation and status of action- use RAG - red - risk still outstanding no mitigation; amber- mitigation in place;green - issue avoided
Use summary from work-stream charter
Detail of total vanguard and matched funding
The sum needed from the vanguard funding
Creat an indicative timelibe showing when the funds are needed and what for
Indicate if any future funding will be needed to further support the spend proposed
Describe and confirm that any funding governance guidelines are being followed
Describe and confirm the project management in place to ensure on time delivery of the funded work
Insert name of work-stream
Total funding required to carry out the proposed work, broken down into pay/ non-pay and captial spend. Spend shown over the next 4 years and note of any recurrence each year
The Vanguard / MLaFL component of the about amoutnrequested
Any matched funding for the planned work
Any differences between the current amount requested and work being proposed now and the value proposition
Outline what will take place to implement the change and achieve the objectives
High level timeline showing main milestones
Describe the back-ground - why we need to do this work
what's in and out of scope for this work-stream- include interdependencies
What are the main objectives of the work-stream- what are we trying to achieve
What you will measure to determine success, including a target for each measurement
Statement of the main risks to the work-stream delivering what it sets out to within any time and cost budget outlined

## 1. charter
Workstream/Project Charter - Prevention and Early Intervention
Date |  | 2015-10-17 | Project |  |  | Prevention and Early Intervention |  | Executive Sponsor |  | Rida Elkheir |  | Sponsor
Project Leads |  | Anita CameronSmith | [5 empty] | Project Support
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
There are significant challenges to the future health and wellbeing of our Island population that make the emphasis on prevention and early intervention crucial to a sustainable health and care system. Although overall the island enjoys good health there are significant health inequalities. There are some key modifiable risk factors that are responsible for about 40% of ill health with the leading overall risk being poor diet with smoking a close second. The remaining 60% are a combination of factors, age, genetics, environmental but many being scocio-economic this means that although we are living longer , we are spending more years in poor health, this is particualrly true for those living with deprivation. |  |  | IN | The strategy will be being co-produced with residents, health and social care and voluntary sector to ensure all stakeholders are involved using the My Life toolkit that is being produced. The strategy will encompass building social capital and strengthening communities, primary, secondary and tertiary preventative elements
|  |  | OUT | As prevetion and early intervention is a whole system issue nothing is out of scope, however the strategy will identify specific priority areas for the next two years
Objectives and case for change
The key to sustainable change in any health and social care economy is changing the overall profile of population health. In line with the 5-year forward view, our aim is to shift care and wellbeing to prevention and early intervention agendas. Improving our ability to prevent illness, diagnose, and intervene early before conditions become serious has the potential to improve outcomes and reduce the long-term costs for health and social care services. Social support and strong social capital are particularly important in increasing resilience and promoting recovery from illness (Kings Fund, 2003, 2008) Phase One Preparation Objectives: 1. Workstream governance structures in place 2. Staffing capacity recruited 3. Project plans agreed. Phase Two Delivery Objectives: 1. Co-production of Island Prevention and Early Intervention Strategy 2.Lay Foundation for holistic family wellbeing platform 3.Delivery of e-solutions treatment for those suffering with anxiety and depression through live therapy and online courses 4.Delivery of Local Area Coordination in six neighberhoods by end of March 2016
High-Level Risk Analysis
Measures of Success
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  | Rating
C0-Produced Intrgrated Prevention and early intervention Strategy |  |  |  | A | capacity recruited to produce startegy and do public/stakeholder engament/co-prodution |  |  | Outcomes | Staff back-fill to release capacity |  | flexilble recruitment secondment/fixed term etc. |  | A
Delivery of training programme to lay foundation for family wellbeing platform |  |  |  | A | traning programme plan in place abd delivery underway |  |  | Cost |  |  |  |  | A
x6 Local area coordinators by 31st march 2016 |  |  |  | G | 2nd 3 Local area coordinator recruitment process |  |  | Performance |  |  |  |  | G
Mental health e-solutions |  |  |  | A |  |  |  | Safety
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
Through both our enabler workstreams and the prevention and early intervention workstream we will have a fully integrated strategy which will allow us to provide co-ordinated, efficient and effective prevention and early intervention services on the Island. We will achieve this through;
1- Delivery of local area coordination programme, working within three neighbourhood, Ryde, the Bays, Freshwater
2- Each local area coordinator will work 50 to 65 individuals and their families, to use their gifts, skils and talents to achieve their vision of a happy and full life
3- Introduction of a 'Whole System' family wellbeing platform that has a workforce that is skilled and enabled to deliver support to people to improve health outcomes, this whole system platform will include not just health and social care services but, voluntary, community, lesiure, libaries, workplaces, schools, fire,police, housing, job center plus etc. This will be achieved through robust training and development programmes.
Approach
Activities- timeline
2016/17 plans are part of phase two, and will be shaped after determining priority projects in December

## Workstream schedule
Prevention and Early Intervention
Project Number | Milestone Narrative / Task | Links with | Follows on from | Start Date | End Date | Status | Responsible Person | Week Commencing Dates
|  |  |  | 2015-09-21 | 2016-03-31 | time axis 2015-09-21 to 2016-09-19
1 - Prevention Strategy | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Procure resource to develop and produce Prevention strategy: Consultant identified, specification written costs agreed (three days a week - Work being carried out at risk). | Localities/WISR/Commissioning/Comms &Engagement | confirmation of funding | 2015-09-28 | 2015-12-05 |  | Anita Cameron-Smith | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Consultant to undertake desk-top research on all strategies, are priorities already met? Are there any gaps? | Localities/WISR/Commissioning/Comms &Engagement | confirmation of funding | 2015-10-01 | 2015-10-22 |  | Kim Ball | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Identify resource and workplan for cost benefit/SROI for preventative strategy ( Linking with Sharon Kingsman and the Evaluation & Measurement work-stream's work on cost- benefit analysis). | Localities/WISR/Commissioning/Comms &Engagement | confirmation of funding | 2015-10-01 | 2015-11-15 |  | Mike Bulpitt | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Development of work-plan for prevention strategy work. |  |  | 2015-09-28 | 2015-11-05 |  | Anita Cameron-Smith |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continue strategy development workshops ( 1/ 6 completed - part of work-plan)- dates to be confirmed. | localities/Comms &Engagement /commissioning |  | 2015-10-08 | 2015-11-08 |  | Anita Cameron-Smith | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Stakeholder Engagement to co-produce strategy - using the Co-production/engagement toolkit produced by Comms/Engagement work stream to plan type of engagement, how frequent, and with who | localities/Comms &Engagement /commissioning | confirmation of funding | 2015-11-01 | 2015-12-31 |  | Kim Ball | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Initial Session to be held with the prevention leadership ( 5th Nov) in order to identify proposed priority projects for 2016/17 value proposition |  |  | 2015-11-05 | 2015-11-05 |  | Kim Ball | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Finalise the four to six priorities |  |  | 2015-11-13 | 2015-11-20 |  | Rida Elkheir/ Mike Bulpitt | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Identify resource within the PMO to assist creation of 16/17 Value Proposition |  |  | 2015-11-06 | 2015-11-13 |  | Mike Bulpitt | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Create the 16/17 Value proposition for the prioritised projects |  |  | 2015-11-20 | 2015-12-31 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Draft prevention strategy created by 3/ Jan. |  |  | 2015-11-06 | 2016-01-03 |  | Kim Ball | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Draft strategy to be circulated to all relevant boards. |  |  | 2016-01-03 | 2016-01-03 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Prevention & Early Intervention strategy signed-off. |  |  | 2016-01-04 | 2016-01-31 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2- Family Wellbeing Platform | [7 empty] | 2015-09-21: FALSE
| Create a draft training programme for the Family Wellbeing Platform |  |  | 2015-10-01 | 2015-10-08 |  | Zoryna O'Donell | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Sign off the final training programme for Family Wellbeing Platform- depending on funding. |  |  | 2015-10-30 | 2015-10-30 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Deliver 'Live Well' 1 day workshops x 4 for senior managers of public health, libraries, health visitors, education, housing associations etc |  |  | 2015-10-12 | 2015-12-15 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Workshop 1 to develop a whole system approach |  |  | 2015-10-12 | 2015-10-12 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Workshop 2 to develop a pathway, workforce fit for purpose. |  |  | 2015-11-09 | 2015-11-09 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Workshop 3 to develop specialist areas |  |  | 2015-11-15 | 2015-11-30 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Workshop 4 to monitor caseload and data. |  |  | 2015-11-15 | 2015-12-15 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Set up motivational interviewing e-learning training for the practitioners to effectively deal with client's resistance. |  |  | 2015-10-01 | 2015-12-31 |  | Zoryna O'Donell | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Deliver 'making every contact count', training for trainers |  |  | 2015-10-01 | 2015-12-31 |  | Zoryna O'Donell | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Deliver making every contact count training programme - face to face |  |  | 2015-10-01 | 2015-12-31 |  | Zoryna O'Donell | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Offer making every contact counts training - online |  |  | 2015-10-01 | 2015-12-31 |  | Zoryna O'Donell | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Promoting behaviour change training - delivered by BHF, one - 2 day course for 25 participants ( TBC once funding is confirmed). |  |  | TBC | TBC |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continue & Begin Fast Coaching- Scoping and Adaptation in health improvement context |  |  | 2015-12-15 | 2015-12-16 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continue & Begin Fast Coaching® Scoping and Adaptation workshop - scoping and adaptation work |  |  | 2016-01-26 | 2016-02-02 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continue & Begin Fast Coaching® Scoping and Adaptation workshop - front line staff | Localities/WISR/Commissioning/Comms &Engagement /workforce development |  | 2016-02-03 | 2016-02-03 |  | Heather Rowell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continue & Begin Fast Coaching® Scoping and Adaptation workshop - train the trainer |  |  | 2016-03-01 | 2016-03-02 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Go live and support 1500 families over a 12 months period to make sustainable life style changes - include within 2016/17 value proposition |  |  | 2016-01-01 | 2017-03-31 |  | Zoryna O'Donell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
| Phase 1: Cohort trained, start implementing health conversation, brief intervention and sign-posting |  |  | 2016-01-01 | 2017-01-01 |  | Zoryna O'Donell | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| Phase 2: (funding dependant), identify moderate to high risk families to refer to live well programme. |  |  | 2016-04-01 | 2017-03-31 |  | Zoryna O'Donell | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| Phase 3: Pilot and evaluate the 2016/17 and expand the programme to 5000 families |  |  | 2016-09-01 | 2017-03-31 |  | Zoryna O'Donell | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
3- Local Area Coordination
| Monthly Local Area Coordination Leadership Steering Group (Ongoing)- meets monthly |  |  | 2014-10-20 | 2016-03-31 |  | Anita Cameron-Smith | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Recruitment of 1st cohort of 3 Local Area Coordinators |  |  | 2015-09-01 | 2015-09-27 |  | Heather Rowell | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Induction - 3 months induction |  |  | 2015-09-27 | 2015-12-31 |  | Heather Rowell | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Introductions to vulnerable people for support |  |  | 2015-10-15 | 2015-12-31 |  | Heather Rowell | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Community neighbourhood asset mapping |  |  | 2015-10-15 | 2015-12-31 |  | Heather Rowell | 2015-10-05: FALSE; 2015-10-12: TRUE; 2015-10-19: TRUE; 2015-10-26: TRUE; 2015-11-02: TRUE; 2015-11-09: TRUE; 2015-11-16: TRUE; 2015-11-23: TRUE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: TRUE; 2015-12-28: TRUE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE
| Recruitment of service manger/ PM for Local area co-ordination( Heather Rowell) |  |  | 2015-10-15 | 2015-10-31 |  | Heather Rowell | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Recruitment of 2nd cohort of 3 Local Area Coordinators |  |  | 2015-12-01 | 2016-01-31 |  | Heather Rowell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Induction - 3 months induction |  |  | 2016-02-01 | 2016-04-30 |  | Heather Rowell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Introductions to vulnerable people for support |  |  | 2016-03-15 | 2016-03-31 |  | Heather Rowell | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Community neighbourhood asset mapping |  |  | 2015-10-15 | 2015-12-31 |  | Heather Rowell | 2015-10-05: FALSE; 2015-10-12: TRUE; 2015-10-19: TRUE; 2015-10-26: TRUE; 2015-11-02: TRUE; 2015-11-09: TRUE; 2015-11-16: TRUE; 2015-11-23: TRUE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: TRUE; 2015-12-28: TRUE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE; 2016-03-14: FALSE; 2016-03-21: FALSE
| Ongoing evaluation and monitoring of local area co-ordination to inform the next funding draw down for NCM support to go to 12 LACs. |  |  | 2016-02-15 | 2016-04-30 |  | Chad Oatley | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Plan to recruit the remaining 6 local area coordinators to cover whole island- include in 2016/17 value propositions |  |  | 2016-02-15 | 2016-04-15 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| 12 area local area coordinators are in place supporting whole island |  |  | 2016-04-01 | 2017-03-31 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
4- E-Health mental health solutions | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Undertake an options appraisal to review feasible options such as scaling down, looking at other solutions etc. 26 Oct – 7th Nov – CAROL FOLEY |  |  | 2015-11-01 | 2015-12-31 |  | Carol Folet/ Anita | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Recommended options are taken to the MY Life Board – Nov 2015 |  |  | 2015-11-01 | 2015-12-31 |  | Carol Folet/ Anita | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Take forward the procurement waiver - After board approval |  |  | 2016-01-01 | 2016-03-31 |  | Carol Folet/ Anita | 2015-12-28: TRUE; 2016-01-04: TRUE; 2016-01-11: TRUE; 2016-01-18: TRUE; 2016-01-25: TRUE; 2016-02-01: TRUE; 2016-02-08: TRUE; 2016-02-15: TRUE; 2016-02-22: TRUE; 2016-02-29: TRUE; 2016-03-07: TRUE; 2016-03-14: TRUE; 2016-03-21: TRUE; 2016-03-28: TRUE
| Take forward the procurement waiver - After board approval |  |  | 2016-01-01 | 2016-03-31 |  | Carol Folet/ Anita | 2015-12-28: TRUE; 2016-01-04: TRUE; 2016-01-11: TRUE; 2016-01-18: TRUE; 2016-01-25: TRUE; 2016-02-01: TRUE; 2016-02-08: TRUE; 2016-02-15: TRUE; 2016-02-22: TRUE; 2016-02-29: TRUE; 2016-03-07: TRUE; 2016-03-14: TRUE; 2016-03-21: TRUE; 2016-03-28: TRUE
| Procure e-health |  |  | 2016-01-01 | 2016-03-31 |  | Carol Folet/ Anita | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5-Influencing, engagement and cultural change | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Submit consultant procurement waiver |  |  | 2015-10-20 | 2015-10-20 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Procurement waiver to employ consultants signed off |  |  | 2015-10-20 | 2015-10-31 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Agree contract T&C with each consultant |  |  | 2015-10-31 | 2015-10-31 |  | Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Develop engagement work-plan for each consultant |  |  | 2015-11-05 | 2015-11-12 |  | Rida Elkheir | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Deliver engagement programme |  |  | 2015-11-13 | 2016-03-30 |  | consultants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Measure/audit effectiveness |  |  | 2016-03-30 | 2016-04-30 |  | Rida Elkheir | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[8 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 - Finance | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Continuously gather information on costs of back-fill of Public Health posts. |  |  | 2015-09-01 | 2016-03-31 |  | Rida Elkheir | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Estimate cost of any venues, learning materials, refreshments, local promotions and staff back fill costs and to-date unconfirmed training packages. |  |  | 2015-09-01 | 2016-03-31 |  | Zoryna O'Donell | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 - Phase 2 priorities for 2016/17 | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Homelessness | [6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Initial discussion of priorities on 5th Nov with voluntary sector and adult social care |  |  | 2015-11-05 | 2015-11-05 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: TRUE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: FALSE; 2015-12-07: FALSE; 2015-12-14: FALSE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Explore/ assess need via public health data (joint strategic needs assessments), ready for the 2016/ 17 value proposition |  |  | 2015-12-01 | 2015-12-15 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Identify what's already in place i.e. current capacity |  |  | 2015-12-01 | 2015-12-15 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Mental Health | [5 empty] | Rida Elkheir/ Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Discuss and determine which area of mental health |  |  | 2015-11-05 | 2015-11-05 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: TRUE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: FALSE; 2015-12-07: FALSE; 2015-12-14: FALSE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Take work forward into the value proposition |  |  | 2015-11-15 | 2015-12-15 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: TRUE; 2015-11-16: TRUE; 2015-11-23: TRUE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Shared lives services | [5 empty] | Rida Elkheir/ Anita Cameron-Smith | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Determine way forward and costs involved at the meeting on 5th Nov |  |  | 2015-11-05 | 2015-11-05 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-12: FALSE; 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: TRUE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: FALSE; 2015-12-07: FALSE; 2015-12-14: FALSE; 2015-12-21: FALSE; 2015-12-28: FALSE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE
| Meeting with CEO of shared lives |  |  | 2016-01-01 | 2016-01-07 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: FALSE; 2015-12-07: FALSE; 2015-12-14: FALSE; 2015-12-21: FALSE; 2015-12-28: TRUE; 2016-01-04: TRUE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE; 2016-02-15: FALSE; 2016-02-22: FALSE; 2016-02-29: FALSE; 2016-03-07: FALSE; 2016-03-14: FALSE; 2016-03-21: FALSE; 2016-03-28: FALSE; 2016-04-04: FALSE
| Appraise and include into the 2016/17 value proposition |  |  | 2015-12-01 | 2015-12-31 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: TRUE; 2015-12-28: TRUE; 2016-01-04: FALSE; 2016-01-11: FALSE; 2016-01-18: FALSE; 2016-01-25: FALSE; 2016-02-01: FALSE; 2016-02-08: FALSE
| Community assets; transformation plans to shift services, scope and plan 2016/17 |  |  | 2015-12-01 | 2016-03-31 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: TRUE; 2015-12-28: TRUE; 2016-01-04: TRUE; 2016-01-11: TRUE; 2016-01-18: TRUE; 2016-01-25: TRUE; 2016-02-01: TRUE; 2016-02-08: TRUE
| Voluntary sector activities - transformation plans, what steps to take, scope and plan 2016/17 |  |  | 2015-12-01 | 2016-03-31 |  | Rida Elkheir/ Anita Cameron-Smith | 2015-10-19: FALSE; 2015-10-26: FALSE; 2015-11-02: FALSE; 2015-11-09: FALSE; 2015-11-16: FALSE; 2015-11-23: FALSE; 2015-11-30: TRUE; 2015-12-07: TRUE; 2015-12-14: TRUE; 2015-12-21: TRUE; 2015-12-28: TRUE; 2016-01-04: TRUE; 2016-01-11: TRUE; 2016-01-18: TRUE; 2016-01-25: TRUE; 2016-02-01: TRUE; 2016-02-08: TRUE
8 - Programme Management, weekly huddles, progress tracking | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Set up weekly workstream meetings - huddle meetings in diary, adult social care, Mike, Kim, Heather, Zoryna - FIRST MEETING on 29th Oct |  |  | 2015-10-29 | 2015-10-30 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| On-going weekly meetings to track progress, escalate issues |  |  | 2015-10-29 | 31/11/2016 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
[8 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[8 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2016/17 value proposition

## 3. risks & issues log
Status Key: |  |  | Prevention and Early Intervention -Risk & Issue Log
Closed | [8 empty] | LAST UPDATED
On schedule
Behind schedule
RISK - An uncertain event that, if it occurs, has a positive or negative effect on the prospects of achieving project objectives. ISSUE - A relevant event that has happened, was not planned, requires management action and has had a negative effect on the Programme, Project or workstream.
Item No | Date Raised | Risk or Issue? | Raised By | Description | Mitigation | Escalation To | Resolution Date | Owner | Status
1 | 2015-09-15 | 1 | Prevention Leadership group | lack of capcity to do full co-production for strategy | consultant capcity identified can recruit as soon as funding confirmed |  | 2015-10-19 | Anita cameron-Smith | closed
2 | 2015-09-15 | 2 | Prevention Leadership group | Programme management support | JD written, expression of interest ad ready, can be recruited to through secondement/fixed term contract on confirmation of funding through community action IW |  |  | M. Bulpitt/ACS
3 | 2015-10-01 | 3 | LAC leadership Group | LAC programme/Line manager to be costs have not been allocated to BCF LAC | PH have been supporting the programme with leadership and management support to date, this will be formalised with the secondment of Heather Rowell to LAC programme as 1WTE programme manager |  |  | Anita Cameron Smith
4 | 2015-10-21 | 4 | MLaFL/CCG/PH | Costs for e-solutions for mental health in orginal Value proposition do not reflect the whole costs of 1500 licences for big-white-wall | CCG/PH will prociuce an options appraisal for Prevention leadership group on way forward |  |  | ACS/Carol Foley
5 | 2014-10-21 | 5 | Prevention leadership group | Have gone 'at risk' on consultant cost for prevention strategy | MLaFL governance/financial templates agreed for release of funding |  |  | ACS
6 | 2015-10-23 | 6 | Prevention Leadership group | Need clarification of overall PMO for the workstream | ACS/Mike Bulpitt currently managing with KM&T support
7 | 1900-01-25 | 7 | Prevention Leadership Group | An estimate for back-fill costs for training has been used, however not all training back-fill costs have been identified, a limit of £60k has been set. There is a risk that there may be over/under demand for back-fill. | ACS/Mike Bulpitt
8
9
10

## 4. key performance indicators
Prevention and Early Intervention
Date updated:
Process KPI's | Outcome KPI's
1- Co-produce Intergrated Prevention and Early Intervention Strategy January 2016
3- Family wellbeing platform
PHASE 1: Delivery of training programme to lay foundation for family wellbeing platform by March 2016
PHASE 2: Go live on 1st April and support families - one year programme
2- Six local area coordinators in post, trained and ready to start supporting vulnerable families by March 2016
Logic Modelling completed, work in progress to determine KPI's

## 5. Finance template
Workstream Name: Finance Template Prevention and Early Intervention
Date |  | 2015-10-20 | [8 empty] | Executive Sponsor 1 |  |  |  |  | Sponsor 2
Worsktream Lead | [10 empty] | Workstream Support
Workstream summary and outcomes | [10 empty] | Timeline and key funding milestones
We will deliver in 2015-16 an integrated, co-produced, prevention and early intervention strategy. We will have undertaken training for prevention and early intervention stakeholders to change the cultural mind-set. We will also have completed and evaluated pilots for Local Area Coordinators and mental health e-solutions. Through this we will achieve the following outcomes for the person: People are able to speak up and self advocate. People are managing their own health better. People are able to self direct the services they want to live independently. People are supported into work, volunteering or training. People are supported to make home safer. More people will feel supported with their emotional wellbeing More people will be able to access evidenced based psychological therapies quicker and 24/7 More people will recover and be empowered to maintain their emotional wellbeing People will have reduced work absence due to mental health Improved choice of services | [10 empty] | (Use this space to outline when funding will be needed and what for - see example below) Funding request must be in quarterly phasing Show what key deliverbales (outputs) will be in each quarter If possible, show what key person-centred outcomes will be in each quarter
Total funding requirements for delivery
(Use this space to provide as much detail as possible for the money you would spend such as pay bands, FTE numbers, capital expenditure etc)
Revenue (all funding sources) | 2015-16 |  |  |  | 2016-17 | 2017-18 | 2018-19 | Total | Recurring p.a. | 2019+ non-recurrent
| Q1 | Q2 | Q3 | Q4
Pay sub-total | 25000 | 25000 | 98244.3399 | 118244.3399 | 217625.3423 | 0 | 0 | 484114.0221
Non-pay sub-total | 12500 | 12500 | 43582 | 192448 | 450000 | 0 | 0 | 711030
Capital sub-total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand total | 37500 | 37500 | 141826.3399 | 310692.3399 | 667625.3423 | 0 | 0 | 1195144.0221
This funding request | [10 empty] | Future funding request
(Note: this will either match the 'total funding requirements for delivery' amount in the box above, or it may be partial) | [10 empty] | Use this space to explain next phase funding requirements (Note: this box plus the 'Funding request' box will equate to the 'total funding requirements for delivery' box)
Revenue (Vanguard funding source) | 2015-16 |  |  |  | Total | Recurring p.a. |  |  |  |  | Revenue (MLAFL future funding source) | 2016-17 |  |  |  | Total | 2017-18 | 2018-19 | Recurring p.a. | 2019+ non-recurrent
| Q1 | Q2 | Q3 | Q4 | [7 empty] | Q1 | Q2 | Q3 | Q4
Pay sub-total | 0 | 0 | 63244.3399 | 63244.3399 | 126488.6799 | [5 empty] | Pay sub-total | TBC | TBC | TBC | TBC | 117625.3423
Non-pay sub-total | 0 | 0 | 31082 | 179948 | 211030 | [5 empty] | Non-pay sub-total | TBC | TBC | TBC | TBC | 450000
Capital sub-total | 0 | 0 | 0 | 0 | 0 | [5 empty] | Capital sub-total |  |  |  |  | 0
Grand total | 0 | 0 | 94326.3399 | 243192.3399 | 337518.6799 | [5 empty] | Grand total | TBC | TBC | TBC | TBC | 567625.3423 | TBC | TBC
Governance arrangements: funding | [10 empty] | Governance arrangements: project management
Confirmation that governance arrangements comply with that of the host organisation e.g., NHS procurement guidelines, financial management rules etc Confirmation that this document meets MLAFL reporting requirements Confirmation that all other funding sources are in place Confirmation that affordability of any ongoing costs have been confirmed (for your own organisation or affected partners) Confirmation that consideration has been given to the route for any consultancy spend, and timescales ahve been adjusted to account for it. Confirmation that the New Care Models' national support package has been reviewed and used where appropriate | [10 empty] | Confirmation that the project management resources are in place to deliver the project
| Sig: Host organisation/s Finance Director: |  |  |  | Sig: Executive sponsor: | [6 empty] | Sig: Executive sponsor: |  |  |  | Sig: Project Lead:
Start recruitment for required resource
Start worsktream activites
Obtain funding from MLAFL board
Procurement of external consultant re developing strategy
Begin delivery of the family wellbeing platform training programme
Back-fill of local capacity time to devlop 16/17 value proposition
Appiont Local Area Coordination Programme Manager
Induction of Ist cohort of Local Area Coordinators
Timeline Nov Dec Jan 16 F eb Mar Apri May Jun July Aug Sept Oct Nov Dec Jan 17 Feb Mar
production of ' 'signed off' prevention strategy
Continue to deliver training programme
Planning for 16/17 delivery based on agreed funding from NCM
continue to deliver LAC programme
Recruit 2nd cohort of Local Area Coordinators
initerim evaluation
Move to delivery phase of 'family wellbeing platform' depending on NCM funding
Recruit final 6 LAC's to bring programme to full capacity -depending on NCM funding
Deliver Strategy priorities - depenant on NCM finding
ongoing evaluation
delivery phase of 'family wellbeing platform' depending on NCM funding
Del;ivery of full capacity LAC programme-depending on NCM funding
Deliver Strategy priorities - depenant on NCM finding
ongoing evaluation

## 6. Finance details
Funding requirements - per project
Workstream Name and Ref number: Prevention and Early Intervention
| Revenue (all funding sources) | 2015-16 |  |  |  | 2016-17 | 2017-18 | 2018-19 | Total | Recurring p.a. | 2019+ non-recurrent
|  | Q1 | Q2 | Q3 | Q4
Pay
| Development and Implementation of the prevention strategy- Project manager |  |  | 22588.0044 | 22588.0044 | 0 | 0 | 0 | 45176.0087
| Development and Implementation of the Family Wellbeing Platform- Project manager |  |  | 11951.6098 | 11951.6098 | 47806.4393 |  |  | 71709.659
| Project support officer |  |  | 6204.7257 | 6204.7257 | 24818.903 |  |  | 37228.3545
| Aggregate back-fill for Senior Public Health Practitioner level (equivolent to 1.0 WTE) |  |  | 22500 | 22500 | 45000 |  |  | 90000
| BCF (Local Area Coordinators) | 25000 | 25000 | 25000 | 25000 | 100000 |  |  | 200000
| Clinician time engagement |  |  | 10000 | 30000 |  |  |  | 40000
| Sub-total | 25000 | 25000 | 98244.3399 | 118244.3399 | 217625.3423 | 0 | 0 | 484114.0221
Non-pay
| Mental Health e-solutions |  |  | 0 | 46000 |  |  |  | 46000
| Be You / Live Well workshops (four workshops) |  |  | 2060 | 2060 |  |  |  | 4120
| Motivational Interviewing training |  |  | 6822 |  |  |  |  | 6822
| Promoting Behaviour Change |  |  | 1000 | 2000 |  |  |  | 3000
| Continue and begin 'Fast Coaching' workshops |  |  | 1200 |  |  |  |  | 1200
| Continue and begin 'Fast Coaching' for front-line staff |  |  | 0 | 3888 |  |  |  | 3888
| Continue and begin 'Fast Coaching' train the trainers (accredited) |  |  | 0 | 15000 |  |  |  | 15000
| Clinical engagement about MLAFL and Family Platform |  |  | 10000 | 30000 |  |  |  | 40000
| Family Wellbeing Platform training programme: backfill, training & venue hire |  |  | 0 | 46000 |  |  |  | 46000
| MLAFL overheads (inc venue hire, printing, learning materials) |  |  | 10000 | 25000 |  |  |  | 35000
| Back-fill support for particpants attending workshops (voluntary, library, health visitors, housing associations) |  |  | 0 | 10000 |  |  |  | 10000
| Local Area Coordinators (additional 6 WTE to cover whole Island) |  |  |  |  | 0 |  |  | 0
| Delivery of the Family Platform (1500 families supported for one year) |  |  |  |  | 450000 |  |  | 450000
| Family Platform | 12500 | 12500 | 12500 | 12500 |  |  |  | 50000
| Sub-total | 12500 | 12500 | 43582 | 192448 | 450000 | 0 | 0 | 711030
Capital
N/A
| Grand Total | 37500 | 37500 | 141826.3399 | 310692.3399 | 667625.3423 | 0 | 0 | 1195144.0221 | 0 | 0
| Revenue (Vanguard funding source) | 2015-16 |  |  |  | 2016-17 | 2017-18 | 2018-19 | Total | Recurring p.a. | 2019+ non-recurrent
|  | Q1 | Q2 | Q3 | Q4
Pay
| Development and Implementation of the prevention strategy- Project manager |  |  | 22588.0044 | 22588.0044 | 0 | 0 | 0 | 45176.0087
| Development and Implementation of the Family Wellbeing Platform- Project manager |  |  | 11951.6098 | 11951.6098 | 47806.4393 |  |  | 71709.659
| Project support officer |  |  | 6204.7257 | 6204.7257 | 24818.903 |  |  | 37228.3545
| Aggregate back-fill for Senior Public Health Practitioner level (equivolent to 1.0 WTE) |  |  | 22500 | 22500 | 45000 |  |  | 90000
| Sub-total | 0 | 0 | 63244.3399 | 63244.3399 | 117625.3423 | 0 | 0 | 244114.0221
Non-pay
| Mental Health e-solutions | 0 |  | 0 | 46000 |  |  |  | 46000
| Be You / Live Well workshops (four workshops) | 0 |  | 2060 | 2060 |  |  |  | 4120
| Motivational Interviewing training | 0 |  | 6822 |  |  |  |  | 6822
| Promoting Behaviour Change | 0 |  | 1000 | 2000 |  |  |  | 3000
| Continue and begin 'Fast Coaching' workshops | 0 |  | 1200 |  |  |  |  | 1200
| Continue and begin 'Fast Coaching' for front-line staff | 0 |  | 0 | 3888 |  |  |  | 3888
| Continue and begin 'Fast Coaching' train the trainers (accredited) | 0 |  | 0 | 15000 |  |  |  | 15000
| Clinical engagement about MLAFL and Family Platform | 0 |  | 10000 | 30000 |  |  |  | 40000
| Family Wellbeing Platform training programme: backfill, training & venue hire | 0 |  | 0 | 46000 |  |  |  | 46000
| MLAFL overheads (inc venue hire, printing, learning materials) | 0 |  | 10000 | 25000 |  |  |  | 35000
| Back-fill support for particpants attending workshops (voluntary, library, health visitors, housing associations) | 0 |  | 0 | 10000 |  |  |  | 10000
| Local Area Coordinators (additional 6 WTE to cover whole Island) | 0 |  |  |  | 0 |  |  | 0
| Delivery of the Family Platform (1500 families supported for one year) | 0 |  |  |  | 450000 |  |  | 450000
| Sub-total | 0 | 0 | 31082 | 179948 | 450000 | 0 | 0 | 661030
Capital
N/A
| Grand Total | 0 | 0 | 94326.3399 | 243192.3399 | 567625.3423 | 0 | 0 | 905144.0221 | 0 | 0
| Revenue (Other funding source/s) | 2015-16 |  |  |  | 2016-17 | 2017-18 | 2018-19 | Total | Recurring p.a. | 2019+ non-recurrent
|  | Q1 | Q2 | Q3 | Q4
Pay
| BCF (Local Area Coordinators) | 25000 | 25000 | 25000 | 25000 | 100000 |  |  | 200000
| Clinician time engagement |  |  | 10000 | 30000 |  |  |  | 40000
| Sub-total | 25000 | 25000 | 35000 | 55000 | 100000 | 0 | 0 | 240000
0
| Non-pay | [7 empty] | 0
| Family Platform | 12500 | 12500 | 12500 | 12500 |  |  |  | 50000
| Sub-total | 12500 | 12500 | 12500 | 12500 |  |  |  | 50000
Capital
N/A
Sub-total
| Grand Total | 37500 | 37500 | 47500 | 67500 | 100000 | 0 | 0 | 290000 | 0 | 0
| Savings from this project | Savings in the original funding request in value proposition | 2015-16 | 2016-17 | Any descrepencies between the value proposition and the proposed savings | Explanation for any revisions
Pay
| N/A | 0 | 0 | 0 | None
| Sub-total | 0 | 0 | 0
Non-pay
| Local Area Coordinators |  | 312500 | 1250000 | None
| Mental Health e-solutions |  | 112000 | 112000 | None
| Sub-total | 0 | 424500 | 1362000
Capital
| N/A | 0 | 0 | 0 | None
| Sub-total | 0 | 0 | 0
| Grand Total | 0 | 424500 | 1362000
| Comparison with value proposition |  | Original funding request in value proposition | First release | This request | Balance remaining* | Where is the balance going? (Which budget)
Pay
| Project Support |  | 81000 | 81000 | 81488.6799 | -488.6799
| Backfill for Senior PH Practitioner |  | 0 | 0 | 45000 | -45000
| Sub-total |  | 81000 | 81000 | 126488.6799 | -45488.6799
Non-pay
| Mental Health e-licenses |  | 46000 | 46000 | 46000 | 0
| Live Well Programme |  | 175000 | 175000 | 165030 | 9970
| Sub-total |  | 221000 | 221000 | 211030 | 9970
| Grand Total |  | 302000 | 302000 | 337518.6799 | -35518.6799
[*Narrative explaining the difference]
Sig: Executive sponsor:
Sig: Workstream lead: