## Instructions
How to use this document
Overview The purpose of this document is to provide standard project management and funding request templates for use across the My Life a Full Life programme. These documents will be used by work-stream leads and sponsors to: - request funding from the MLaFL board in line with the requested Vanguard funding - provide assurance to the board that the delivery of benefits is being managed using a defined methodology - form the basis of weekly project management office ( PMO) meetings to track, support and escalate work-stream delivery See instructions below on how to complete these templates.
Tab | How it needs to be completed | Who needs to sign-off
1. Charter | One Charter is to be completed for the entire workstream | MLaFL board
2. Workstream schedule | One workstream schedule must be completed for each workstream | MLaFL board
3. Risks & issues log | One Risks & issues log must be completed for each work-stream | MLaFL board
4. Key Performance indicators | KPIs as required by each work-stream | MLaFL board
5. Finance Template | One template for each work-stream | MLaFL board
6. Finance Details | One template for each project - add tabs as required | MLaFL board
1. Charter | Guidance notes for the work-stream charter
2. Workstream schedule | Guidance notes for the work-stream schedule
3. Risks & issues log | Guidance notes for the Risks& issues log
4. Key Performance indicators | Guidance notes for KPIs
Multiple KPIs may be required
5.Finance template | Guidance on completign the finance template
6.Finance details | Guidance for completing the finance details document
work-stream title
actions/ tasks, owners , start end dates. Use links and 'foolows on from ' to indicate relations to other tasks
cells auto populate based on dates input
Red line shows current date- use 'back spikes to show delays.
work-stream name
Risk- a possible enent or circumstanced that will negatively impact work-stream delivery schedule. Issue- a problem that has occured
Action to be taken to address issue or mitigate risk
Action owner, due date, escalation and status of action- use RAG - red - risk still outstanding no mitigation; amber- mitigation in place;green - issue avoided
Use summary from work-stream charter
Detail of total vanguard and matched funding
The sum needed from the vanguard funding
Creat an indicative timelibe showing when the funds are needed and what for
Indicate if any future funding will be needed to further support the spend proposed
Describe and confirm that any funding governance guidelines are being followed
Describe and confirm the project management in place to ensure on time delivery of the funded work
Insert name of work-stream
Total funding required to carry out the proposed work, broken down into pay/ non-pay and captial spend. Spend shown over the next 4 years and note of any recurrence each year
The Vanguard / MLaFL component of the about amoutnrequested
Any matched funding for the planned work
Any differences between the current amount requested and work being proposed now and the value proposition
Outline what will take place to implement the change and achieve the objectives
High level timeline showing main milestones
Describe the back-ground - why we need to do this work
what's in and out of scope for this work-stream- include interdependencies
What are the main objectives of the work-stream- what are we trying to achieve
What you will measure to determine success, including a target for each measurement
Statement of the main risks to the work-stream delivering what it sets out to within any time and cost budget outlined

## 1. Charter
Workstream/Project Charter - Whole Integrated System Review (WISR) - Draft subject to Board Approval
Date |  | 2015-09-01 | Project |  |  | Whole Integrated System Review |  | Sponsor 1 |  | Helen Shields |  | Sponsor 2 | TBC
Project Lead |  | Martin Robinson | Project Manager |  |  | To be recruited |  | Project Support |  | Cathy Budden
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
MLAFL Partnership has built a joint vision of local health and care services at a high level to meet the challenges of the future and it has developed a new care model for the Island. We now need to develop the more detailed care pathways in line with this model which will shape our future service provison. To do this, we need to redesign whole system pathways and undertake a whole integrated system review. The Whole Integrated System Review will help us to understand how current services are delivered, impact of redesigning services and how they should be delivered in the future. The Review will build on the work already in progress and will be undertaken in phases, enabling earlier implementation of 'quick wins' |  |  | IN | The scope of the review will include health, social care services, commissioned public health services and related voluntary sector services across the whole integrated system. This will take into account the whole patient pathway including prevention, community healthcare, social care, primary and secondary care. The scope will include reviewing the flow of individuals into and off the Island and services delivered on the mainland, including providers from all market sectors.
|  |  | OUT | Everything is within scope.
Objectives
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators - DRAFT |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls |  |  | Rating
Successful procurement of review partners |  |  |  | 10% | 100% |  |  | Outcomes | Review progress delayed /derailed by public/stakeholder opinion |  | Co production, stakeholder ownership, strong public and stakeholder engagement. |  |  | A
Development of service models and identifying savings |  |  |  | 0% | 100% |  |  | Cost | Whole system savings not realised |  | Careful modelling of future service model budgets |  |  | G
Successful implementation of Communication and Engagement Strategy, including Public Consultation |  |  |  | 0% | 100% |  |  | Performance | Failure to deliver outcomes |  | Ongoing monitoring and evaluation of workstream |  |  | G
Development of costed implementation plans |  |  |  | 0% | 100% |  |  | Safety | Service provision compromised |  | Careful mapping and understanding of proposed service provision |  |  | A
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
An external partner will be engaged to support the WISR Programme Board in undertaking this review. This will be a dynamic and fast-paced review, that will focus on getting to pre-consultation business case within 7 months.
The approach will be to:
• Support co-production
• Engage a partner to support the WISR Programme in undertaking the whole integrated system review
• Develop and implement a comprehensive communication and engagement strategy
• Develop a case for change
• Develop a joint commissioning strategy
• Develop new models of care to provide safe and sustainable services within the Island's resources
• Undertake full formal public consultation on potential new models
• Develop costed implementation plans on agreed future model
Approach
Activities
The objective is to develop new models of care to provide safe and sustainable services within the Island's resources, which will:
ᴑ Integrate services
ᴑ Reduce reliance on statutory services
ᴑ Are based more in the community/at home
ᴑ Represent a significant shift to prevention
In 2015-16 we will have commenced the Whole Integrated System Review and will be implementing the first tranche of ‘quick wins’ on an ongoing basis to realise efficiencies and to generate stakeholder buy-in in early 2016/17.
Week commenicing 19th October: Logic Modelling completion, explore outcomes, and KPI's