## Instructions
How to use this document
Overview The purpose of this document is to provide standard project management and funding request templates for use across the My Life a Full Life programme. These documents will be used by work-stream leads and sponsors to: - request funding from the MLaFL board in line with the requested Vanguard funding - provide assurance to the board that the delivery of benefits is being managed using a defined methodology - form the basis of weekly project management office ( PMO) meetings to track, support and escalate work-stream delivery See instructions below on how to complete these templates.
Tab | How it needs to be completed | Who needs to sign-off
1. Charter | One Charter is to be completed for the entire workstream | MLaFL board
2. Workstream schedule | One workstream schedule must be completed for each workstream | MLaFL board
3. Risks & issues log | One Risks & issues log must be completed for each work-stream | MLaFL board
4. Key Performance indicators | KPIs as required by each work-stream | MLaFL board
5. Finance Template | One template for each work-stream | MLaFL board
6. Finance Details | One template for each project - add tabs as required | MLaFL board
1. Charter | Guidance notes for the work-stream charter
2. Workstream schedule | Guidance notes for the work-stream schedule
3. Risks & issues log | Guidance notes for the Risks& issues log
4. Key Performance indicators | Guidance notes for KPIs
Multiple KPIs may be required
5.Finance template | Guidance on completign the finance template
6.Finance details | Guidance for completing the finance details document
work-stream title
actions/ tasks, owners , start end dates. Use links and 'foolows on from ' to indicate relations to other tasks
cells auto populate based on dates input
Red line shows current date- use 'back spikes to show delays.
work-stream name
Risk- a possible enent or circumstanced that will negatively impact work-stream delivery schedule. Issue- a problem that has occured
Action to be taken to address issue or mitigate risk
Action owner, due date, escalation and status of action- use RAG - red - risk still outstanding no mitigation; amber- mitigation in place;green - issue avoided
Use summary from work-stream charter
Detail of total vanguard and matched funding
The sum needed from the vanguard funding
Creat an indicative timelibe showing when the funds are needed and what for
Indicate if any future funding will be needed to further support the spend proposed
Describe and confirm that any funding governance guidelines are being followed
Describe and confirm the project management in place to ensure on time delivery of the funded work
Insert name of work-stream
Total funding required to carry out the proposed work, broken down into pay/ non-pay and captial spend. Spend shown over the next 4 years and note of any recurrence each year
The Vanguard / MLaFL component of the about amoutnrequested
Any matched funding for the planned work
Any differences between the current amount requested and work being proposed now and the value proposition
Outline what will take place to implement the change and achieve the objectives
High level timeline showing main milestones
Describe the back-ground - why we need to do this work
what's in and out of scope for this work-stream- include interdependencies
What are the main objectives of the work-stream- what are we trying to achieve
What you will measure to determine success, including a target for each measurement
Statement of the main risks to the work-stream delivering what it sets out to within any time and cost budget outlined

## 1. Charter
Project Charter - Integrated Localities
Date |  | 22nd September | Project |  |  | Integrated Localities |  | Sponsor 1 |  | Michelle Legg
Project Lead |  | Gill Kennett | Project Manager |  |  | Simon Paul |  | Project Support
Background / Overview |  |  |  | Scope |  |  |  | Approach & Activities
Within the scope of Intregrated Locality Team working will be three integrated localities, which will continue to develop and expand. During 2016/17 we will include Independent Providers, Voluntary Sector and specialist services in the teams. This will increase the pace and scale of change. |  |  | IN | The services below have been outlined for Phase 1: * Community Nursing * Continence Services * Long term Social Care * Community Matrons
|  |  | OUT | Phase 2 will continue to expand the integrated working within the community to include non-statutory agencies. It is not anticipated that hospital based acute in-patient services will be included within the programme.
Objectives and case for change
The change delivered by this programme will be the integration of services across agencies to deliver more co-ordinated responsive care to people closer to their homes. The opportunity for co-ordinating care for an ageing population on the Island was first proposed in the 5 year Health and Social Care Vision between the Provider Trust, the Clinical Commissioning Group and the Isle of Wight Council. This has been developed into a programme which supports co-ordination and integration of care to Island Residents. The objective for this programme will be to deliver better integration of services within three localities on the Island to improve co-ordination for people requiring more complex care and to enable identification and earlier intervention for people at risk of crisis or rapidly advancing ill health. Success will be not measured just through less non-elective admissions to hospital or permenant admission to nursing or residential care but also through people being given the information and advice they need to manage their conditions. The Island's demographic means that we need to develop care that is more intuitive to peoples needs and can be accessed in a timely way. Support from Vanguard and interaction with other Vanguard sites will enable the Island to deliver this model of care more quickly than without the support.
Measures of Success | [7 empty] | High-Level Risk Analysis
Key Performance Indicators |  |  |  | Current State | Future State |  |  | Indicators | Risk |  | Controls | Rating
Greater resilience and cross working of staff |  |  |  | Agreement that this is the best model not yet fully implemented | Integrated teams delivering care across agencies sharing skills to strengthen the workforce |  |  | Outcomes | Cynicism and barriers to integration; lack of project resource capacity; ICT; |  | Partners fully signed up to the programme, project teams in place to deliver | Red
Existing performances matched if not improved |  |  |  | Complex model | Shared performance targets joint accountablity for provision of care - better care delivery |  |  | Cost | Saving targets not achieved, potential of investment not realised |  | Baseline costs established, financial monitoring of integrated teams and measurement against the baseline | Amber
Deliver shared savings across agencies |  |  |  | No agreement | Through a strategic partnership share savings can be identified |  |  | Performance | Failure to deliver quality outcomes |  | Processes / cross skilled training needs identified and fulfilled | Amber
Fit for purpose for future commissioning needs |  |  |  | Traditional mode1 | Opportunity for more cohesive model ie Alliance Contract |  |  | Safety | Critical service provision compromised |  | Map and understand processes | Amber
| sig 1: |  |  | sig2: |  |  | sig 3: |  |  | sig 4:
| sig 5: |  | sig 6: |  |  |  | sig 7: |  |  | sig 8:
Phase 1
Delivery
Scoping
Review of current services and map potential areas of duplication
Develop standard operating procedures, training packages and single management structure
Phase 2
Commissioning and Finance
Agree both short and long term commissioning strategy. Develop formal legal partnership requirement if required.
Phase 2 integration is currently being scoped. Outcomes from this will need to considered within the Whole Integrated System Review
Performance Indicators
Approach
Develop performance metrics to ensure compliance against service, contractual and internal standards
Activities